## Ark1
|  | PLAN |  |  |  |  | DESIGN |  |  |  |  | BUILD |  |  |  |  | LAUNCH
|  | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
PROJECT MANAGER | CLIENT MEETING | PROJECT MANAGEMENT, CONTRACT AND CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT AND CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT AND CUSTOMER CONTACT |  |  |  |  | PROJECT MANAGEMENT AND CUSTOMER CONTACT
PROJECT MANAGER CONTENT DEVELOPER |  | PROJECT START BRAINSTORMING
k
PROJECT MANAGER CONTENT DEVELOPER DESIGNER |  | IDENTIFYING GOALS NEEDS ASSESSMENT PROJECT PLANNING
CONTENT DEVELOPER |  |  |  | CONTENT PLANNING
CONTENT DEVELOPER DESIGNER DEVELOPER | [5 empty] | SITE OUTLINE | SITE STRUCTURE
DESIGNER | [8 empty] | STYLE TILES |  |  | WIREFRAMES
CONTENT DEVELOPER COPYRIGHTER | [8 empty] | TEXT DEVELOPMENT
CONTENT DEVELOPER DESIGNER | [12 empty] | UI PLANNING AND TESTING |  |  |  | UI TESTING
DEVELOPER | [11 empty] | CODING, INTEGRATION AND SITE BUILD |  |  |  |  | CODING, INTEGRATION AND SITE BUILD
DEVELOPER | [17 empty] | CROSS PLATFORM BROWSSER TESTING
DEVELOPER | [18 empty] | VALIDATING
CONTENT DEVELOPER DESIGNER DEVELOPER | [19 empty] | REFINEMENT
PROJECT MANAGER CONTENT DEVELOPER DESIGNER DEVELOPER | [20 empty] | LAUNCH!